**QEP Timeline**

|  |  |  |
| --- | --- | --- |
| **2009**  **Two Years Prior to Affirmation** | | |
| **Jan-Apr** | **Sept** | **Sept-Dec** |
| Initiate topic identification | Select topic | Form QEP Committee and begin detailed development |

|  |  |  |
| --- | --- | --- |
| **2010**  **One year Prior to Reaffirmation** | | |
| **Jan-Aug** | **Sept-Oct** | **Dec** |
| Work on QEP | Submit draft to SACS for feedback | Finalize QEP |

|  |  |  |
| --- | --- | --- |
| **2011**  **Year of Reaffirmation** | | |
| **Feb** | **April 4-6** | **Dec** |
| Submit QEP | Onsite review conducted | Review by the Commission on Colleges |

Revised 9/03/09

|  |  |  |
| --- | --- | --- |
| **2016/2017**  **5th Year Interim Report (includes the QEP Impact Report)** | | |
| **April 25, 2016** | **March 25, 2017** | **June 2017** |
| Notification Letter from President of Commission on Colleges | 5th Year Interim Report due to Commission on Colleges | Review of 5th Year Report from Commission on Colleges |